## Slide 1
Monthly Health Synthesis
S2P implementation portfolio | July 2026
2
projects analyzed
2
projects currently Red
87
average risk score
The portfolio needs recovery governance now, not just routine status reporting.
Project Health Reporting Agent
01

## Slide 2
Both projects are Red, but for different reasons
The portfolio pattern is not one generic delay. UniSan has summary-level schedule distress; Titan has execution and dependency risk beneath a Green summary health flag.
Project Health Reporting Agent
02
Titan
Red
85/100 risk score
The project summary risk level is High.
19 open task(s) are past their planned end date.
3 comments contain blocker or dependency language.
UniSan
Red
88/100 risk score
The workbook summary marks overall schedule health as Red.
The project summary risk level is High.
1 critical or zero-float open task(s) are overdue.

## Slide 3
The common trend is near-term execution pressure
Across both plans, the highest shared signal is not budget. It is schedule execution risk concentrated in near-term and overdue work.
Project Health Reporting Agent
03
Chart: 
| Titan | UniSan
Overdue open tasks | 19 | 25
Near-term risky tasks | 34 | 54
44
open tasks are already overdue
88
near-term tasks need attention

## Slide 4
Emerging risks point to dependencies and data readiness
The comments and evidence rows show external inputs, mappings, workshops, and configuration tasks as the leading sources of delivery risk.
Project Health Reporting Agent
04
Dependency risk
Client or integration inputs are pending, including sample data, field mapping, and workflow details.
Milestone compression
Many tasks due within the next reporting window are incomplete or already marked Red/Yellow.
Plan quality gap
Budget burn and target dates are unavailable or unparseable, reducing executive confidence in commercial health.

## Slide 5
Project-level evidence supports executive escalation
The strongest risks are visible in the generated weekly reports, not inferred from a black-box model.
Project Health Reporting Agent
05
Project
RAG
Key evidence
Recommended focus
Titan
Red
The project summary risk level is High. 19 open task(s) are past their planned end date.
Run an executive recovery review focused on overdue critical work, owners, and revised milestone dates.
UniSan
Red
The workbook summary marks overall schedule health as Red. The project summary risk level is High.
Run an executive recovery review focused on overdue critical work, owners, and revised milestone dates.

## Slide 6
Recommended action is a two-week recovery cadence
The next cycle should turn risk evidence into owned actions, updated dates, and cleaner executive reporting.
Project Health Reporting Agent
06
Hold a recovery review for Red items with PMs, delivery leads, and client owners.
Create a 14-day action plan for overdue and near-term risky tasks.
Convert blocker comments into named actions with owner, due date, and escalation path.
Add budget and burn-rate fields so commercial health can be scored in the next monthly report.
Executive ask
Approve a weekly recovery cadence until both projects return to Amber with dated mitigation plans.